## Sheet1
Task | time axis 2020-09-14 to 2021-01-08
Reports
DOER | bar: 2020-09-14 to 2020-09-25
Background Research | bar: 2020-09-22 to 2020-09-25; 2020-09-28
Context Survey | bar: 2020-09-29 to 2020-10-16
Final Report
Modelling
Watch Blender Tutorials on Fundamentals | bar: 2020-09-14 to 2020-09-28
Model Majority of North Transept | bar: 2020-09-29 to 2020-10-07
Model (Remaining) North Transept Windows | bar: 2020-09-29 to 2020-09-30
Model North Transept Walls | bar: 2020-09-30 to 2020-10-02
Model North Transept Roof | bar: 2020-10-02 to 2020-10-05
Model Butresses | bar: 2020-10-04 to 2020-10-06
Model additional details: Ceiling etc.. | bar: 2020-10-05 to 2020-10-08
Meetings
Alan | bar: 2020-09-15
Bess | bar: 2020-09-17
Website
Unreal Engine